## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
1 | 2/3 | Learn about project, and discuss ideas with group members to make concepts. Start doing mini project SRS. | 2022-10-24 | 2022-11-04 | Closed
2 | 4/5 | Start by researching on vending machine functional requirements(steps and flowcharts of vending machines, drink payment, anti-burglar systems and restocking work etc) | 2022-11-07 | 2022-11-18 | Closed
3 | 6/7 | Do implementation of non-functional requirements and software archtecture. Complete SRS, check/edit for final changes and submit SRS. | 2022-11-21 | 2022-12-02 | Closed
MST + Term Break
4 | 12/13 | Code start up and main menu, dispensing of drinks simulation, simulate drink payment and set up RFID database | 2023-01-02 | 2023-01-13 | Closed
5 | 14/15 | Code burglar system, remote monitoring(using flask app), servicing and restocking. Create test cases for code in sprint 4, and test the test cases to debug. | 2023-01-16 | 2023-01-27 | Closed
6 | 16/17 | Create test cases for sprint 5 and debug. Merge code and test(debug errors). Containerize application. | 2023-01-30 | 2023-02-10 | Closed
Formulas:
End Date = [Start Date]+11
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Create Use Case Diagrams in SRS document | As a Software Developer, I need to define all the different Use Case Diagrams for the Automated Checkout System | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | To Do | Sprint 1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6